## Sheet1
|  |  | OCT | NOV | DEC | JAN
|  | w1 |  |  | Milestone Meeting
|  | w2 |  |  |  | Final Report
w3
|  | w4 | Kick-Off
Target time frame:
• Distribution of project information: 16th October
• Team building: 16th – 20th October
• Kickoff meetings: 21th – 27th October |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9
• Milestone meeting with Professor: 2nd – 6th December
• Deadline Transmission of project report 13th January 2025
• Final presentation & demonstration: 13th – 20th 2025
waterfall, V model, SCRUM, Kanban or other methods
150 hours per person per semester
10 hours per week workload
a.radhakrishnan-nair@oth-aw.de; f.mahmoudi@oth-aw.de; h.korat@oth-aw.de; j.patel@oth-aw.de; k.ghoghari@oth-aw.de; m.uddin5@oth-aw.de; r.italiya@oth-aw.de; v.padmani@oth-aw.de
a.radhakrishnan-nair@oth-aw.de; | f.mahmoudi@oth-aw.de; | h.korat@oth-aw.de; | W1: j.patel@oth-aw.de;; W2: k.ghoghari@oth-aw.de;; W3: m.uddin5@oth-aw.de;; W4: r.italiya@oth-aw.de;; W5: v.padmani@oth-aw.de

## Scrum Plan
Detailed SCRUM Plan
Sprint 0: Kickoff & Setup
Dates: October 28 - November 1
Goal: Complete project setup and team organization.
Tasks:
Hold the project kickoff meeting and align team roles.
Define the product backlog with detailed tasks.
Set up the GitLab repository, Rocket Chat, and access Webots R2023b.
Read “Getting started with Webots” and familiarize the team with the “complete_apartment” scenario in Webots.
Develop a basic understanding of webots Robots
Sprint 1: Environment and Basic Navigation
| Task | PIC
Dates: November 4 - November 15 | 2D Building Layout | Rohan & Jhanvi
Goal: Set up the home environment and establish basic navigation for the mobile robot. | Convert 2D Layout to3D World in Webots Model
Tasks: | Mobile Robot 3D Model | Imad
Configure the Webots environment to resemble the elder person’s home. | Robotic Arm 3D Model | Imad
Implement initial movement functionality for Robot to navigate the home. | Manage Repo and Project mgmt
Test and refine navigation within the defined environment.
Sprint 2: Interaction Between Robots
Dates: November 18 - November 29
Goal: Program interaction between Robotino and Ned.
Tasks:
Develop controllers for Robotino to transport the glass to a predefined position.
Implement initial control for the Ned arm to recognize Robotino’s approach and receive the glass.
Conduct internal testing on interaction protocols between robots.
Milestone Review
Dates: December 2 - December 6
Goal: Present the current progress to Prof. Wiehl.
Deliverables: A demonstration of the home environment setup, basic navigation, and initial robot interaction.
Sprint 3: Task Completion and Advanced Features
Dates: December 9 - December 20
Goal: Complete advanced tasks, including moving the glass and tilting for the elder person to drink.
Tasks:
Program Robotino to transport the glass to the elder’s bedside.
Update Ned’s controller to tilt the glass, allowing liquid flow simulation.
Fine-tune robot behaviors and interaction timing for a smoother demonstration.
Holiday Break
Dates: December 23 - January 5
Note: Limited work due to holiday season.
Final Sprint: Testing and Documentation
Dates: January 6 - January 13
Goal: Complete testing, final adjustments, and finalize project documentation.
Tasks:
Conduct full testing of robot movements and interactions.
Prepare the final project report, including the “Project Management” section.
Create a demo script for the final presentation and practice the demo flow.
Final Presentation & Demonstration
Dates: January 13 - January 20
Goal: Showcase the project’s final implementation to the professor and potentially other stakeholders.